## DSM Input
Project Name |  |  | <NOTE> |  |  | 1. Enter the name of a project in cell '2A'.
Sample | [5 empty] | 2. Enter all task names in column 'A'.
Task Name |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240
a | 1 | bar: 1
b | 2 | bar: 1 to 2
c | 3 | 1: 2; 2. Enter all task names in column 'A'. 10: 1
d | 4 | 3: 2; 2. Enter all task names in column 'A'. 10: 1
e | 5 | bar: 2; 2. Enter all task names in column 'A'. 5
f | 6 | 2: 1; 2. Enter all task names in column 'A'. 5: 2
g | 7 | bar: 1; 3; 2. Enter all task names in column 'A'. 7
h | 8 | 2: 2; 2. Enter all task names in column 'A'. 5: 1; 2. Enter all task names in column 'A'. 12: 1
i | 9 | 2. Enter all task names in column 'A'. 5: 2; 2. Enter all task names in column 'A'. 6: 1
j | 10 | bar: 4; 2. Enter all task names in column 'A'. 7; 2. Enter all task names in column 'A'. 10
k | 11 | 2. Enter all task names in column 'A'. 8: 2; 2. Enter all task names in column 'A'. 12: 2
l | 12 | bar: 2. Enter all task names in column 'A'. 11 to 2. Enter all task names in column 'A'. 12
m | 13 | bar: 2. Enter all task names in column 'A'. 7; 2. Enter all task names in column 'A'. 10; 2. Enter all task names in column 'A'. 13
n | 14 | bar: 2. Enter all task names in column 'A'. 9; 2. Enter all task names in column 'A'. 12 to 2. Enter all task names in column 'A'. 14
o | 15 | bar: 2. Enter all task names in column 'A'. 11; 2. Enter all task names in column 'A'. 13 to 2. Enter all task names in column 'A'. 15
16 | bar: 2. Enter all task names in column 'A'. 16
17 | bar: 2. Enter all task names in column 'A'. 17
18 | bar: 2. Enter all task names in column 'A'. 18
19 | bar: 2. Enter all task names in column 'A'. 19
20 | bar: 2. Enter all task names in column 'A'. 20
21 | bar: 2. Enter all task names in column 'A'. 21
22 | bar: 2. Enter all task names in column 'A'. 22
23 | bar: 2. Enter all task names in column 'A'. 23
24 | bar: 2. Enter all task names in column 'A'. 24
25 | bar: 2. Enter all task names in column 'A'. 25
26 | bar: 2. Enter all task names in column 'A'. 26
27 | bar: 2. Enter all task names in column 'A'. 27
28 | bar: 2. Enter all task names in column 'A'. 28
29 | bar: 2. Enter all task names in column 'A'. 29
30 | bar: 2. Enter all task names in column 'A'. 30
31 | bar: 2. Enter all task names in column 'A'. 31
32 | bar: 2. Enter all task names in column 'A'. 32
33 | bar: 2. Enter all task names in column 'A'. 33
34 | bar: 2. Enter all task names in column 'A'. 34
35 | bar: 2. Enter all task names in column 'A'. 35
36 | bar: 2. Enter all task names in column 'A'. 36
37 | bar: 2. Enter all task names in column 'A'. 37
38 | bar: 2. Enter all task names in column 'A'. 38
39 | bar: 2. Enter all task names in column 'A'. 39
40 | bar: 2. Enter all task names in column 'A'. 40
41 | bar: 2. Enter all task names in column 'A'. 41
42 | bar: 2. Enter all task names in column 'A'. 42
43 | bar: 2. Enter all task names in column 'A'. 43
44 | bar: 2. Enter all task names in column 'A'. 44
45 | bar: 2. Enter all task names in column 'A'. 45
46 | bar: 2. Enter all task names in column 'A'. 46
47 | bar: 2. Enter all task names in column 'A'. 47
48 | bar: 2. Enter all task names in column 'A'. 48
49 | bar: 2. Enter all task names in column 'A'. 49
50 | bar: 2. Enter all task names in column 'A'. 50
51 | bar: 2. Enter all task names in column 'A'. 51
52 | bar: 2. Enter all task names in column 'A'. 52
53 | bar: 2. Enter all task names in column 'A'. 53
54 | bar: 2. Enter all task names in column 'A'. 54
55 | bar: 2. Enter all task names in column 'A'. 55
56 | bar: 2. Enter all task names in column 'A'. 56
57 | bar: 2. Enter all task names in column 'A'. 57
58 | bar: 2. Enter all task names in column 'A'. 58
59 | bar: 2. Enter all task names in column 'A'. 59
60 | bar: 2. Enter all task names in column 'A'. 60
61 | bar: 2. Enter all task names in column 'A'. 61
62 | bar: 2. Enter all task names in column 'A'. 62
63 | bar: 2. Enter all task names in column 'A'. 63
64 | bar: 2. Enter all task names in column 'A'. 64
65 | bar: 2. Enter all task names in column 'A'. 65
66 | bar: 2. Enter all task names in column 'A'. 66
67 | bar: 2. Enter all task names in column 'A'. 67
68 | bar: 2. Enter all task names in column 'A'. 68
69 | bar: 2. Enter all task names in column 'A'. 69
70 | bar: 2. Enter all task names in column 'A'. 70
71 | bar: 2. Enter all task names in column 'A'. 71
72 | bar: 2. Enter all task names in column 'A'. 72
73 | bar: 2. Enter all task names in column 'A'. 73
74 | bar: 2. Enter all task names in column 'A'. 74
75 | bar: 2. Enter all task names in column 'A'. 75
76 | bar: 2. Enter all task names in column 'A'. 76
77 | bar: 2. Enter all task names in column 'A'. 77
78 | bar: 2. Enter all task names in column 'A'. 78
79 | bar: 2. Enter all task names in column 'A'. 79
80 | bar: 2. Enter all task names in column 'A'. 80
81 | bar: 2. Enter all task names in column 'A'. 81
82 | bar: 2. Enter all task names in column 'A'. 82
83 | bar: 2. Enter all task names in column 'A'. 83
84 | bar: 2. Enter all task names in column 'A'. 84
85 | bar: 2. Enter all task names in column 'A'. 85
86 | bar: 2. Enter all task names in column 'A'. 86
87 | bar: 2. Enter all task names in column 'A'. 87
88 | bar: 2. Enter all task names in column 'A'. 88
89 | bar: 2. Enter all task names in column 'A'. 89
90 | bar: 2. Enter all task names in column 'A'. 90
91 | bar: 2. Enter all task names in column 'A'. 91
92 | bar: 2. Enter all task names in column 'A'. 92
93 | bar: 2. Enter all task names in column 'A'. 93
94 | bar: 2. Enter all task names in column 'A'. 94
95 | bar: 2. Enter all task names in column 'A'. 95
96 | bar: 2. Enter all task names in column 'A'. 96
97 | bar: 2. Enter all task names in column 'A'. 97
98 | bar: 2. Enter all task names in column 'A'. 98
99 | bar: 2. Enter all task names in column 'A'. 99
100 | bar: 2. Enter all task names in column 'A'. 100
101 | bar: 2. Enter all task names in column 'A'. 101
102 | bar: 2. Enter all task names in column 'A'. 102
103 | bar: 2. Enter all task names in column 'A'. 103
104 | bar: 2. Enter all task names in column 'A'. 104
105 | bar: 2. Enter all task names in column 'A'. 105
106 | bar: 2. Enter all task names in column 'A'. 106
107 | bar: 2. Enter all task names in column 'A'. 107
108 | bar: 2. Enter all task names in column 'A'. 108
109 | bar: 2. Enter all task names in column 'A'. 109
110 | bar: 2. Enter all task names in column 'A'. 110
111 | bar: 2. Enter all task names in column 'A'. 111
112 | bar: 2. Enter all task names in column 'A'. 112
113 | bar: 2. Enter all task names in column 'A'. 113
114 | bar: 2. Enter all task names in column 'A'. 114
115 | bar: 2. Enter all task names in column 'A'. 115
116 | bar: 2. Enter all task names in column 'A'. 116
117 | bar: 2. Enter all task names in column 'A'. 117
118 | bar: 2. Enter all task names in column 'A'. 118
119 | bar: 2. Enter all task names in column 'A'. 119
120 | bar: 2. Enter all task names in column 'A'. 120
121 | bar: 2. Enter all task names in column 'A'. 121
122 | bar: 2. Enter all task names in column 'A'. 122
123 | bar: 2. Enter all task names in column 'A'. 123
124 | bar: 2. Enter all task names in column 'A'. 124
125 | bar: 2. Enter all task names in column 'A'. 125
126 | bar: 2. Enter all task names in column 'A'. 126
127 | bar: 2. Enter all task names in column 'A'. 127
128 | bar: 2. Enter all task names in column 'A'. 128
129 | bar: 2. Enter all task names in column 'A'. 129
130 | bar: 2. Enter all task names in column 'A'. 130
131 | bar: 2. Enter all task names in column 'A'. 131
132 | bar: 2. Enter all task names in column 'A'. 132
133 | bar: 2. Enter all task names in column 'A'. 133
134 | bar: 2. Enter all task names in column 'A'. 134
135 | bar: 2. Enter all task names in column 'A'. 135
136 | bar: 2. Enter all task names in column 'A'. 136
137 | bar: 2. Enter all task names in column 'A'. 137
138 | bar: 2. Enter all task names in column 'A'. 138
139 | bar: 2. Enter all task names in column 'A'. 139
140 | bar: 2. Enter all task names in column 'A'. 140
141 | bar: 2. Enter all task names in column 'A'. 141
142 | bar: 2. Enter all task names in column 'A'. 142
143 | bar: 2. Enter all task names in column 'A'. 143
144 | bar: 2. Enter all task names in column 'A'. 144
145 | bar: 2. Enter all task names in column 'A'. 145
146 | bar: 2. Enter all task names in column 'A'. 146
147 | bar: 2. Enter all task names in column 'A'. 147
148 | bar: 2. Enter all task names in column 'A'. 148
149 | bar: 2. Enter all task names in column 'A'. 149
150 | bar: 2. Enter all task names in column 'A'. 150
151 | bar: 2. Enter all task names in column 'A'. 151
152 | bar: 2. Enter all task names in column 'A'. 152
153 | bar: 2. Enter all task names in column 'A'. 153
154 | bar: 2. Enter all task names in column 'A'. 154
155 | bar: 2. Enter all task names in column 'A'. 155
156 | bar: 2. Enter all task names in column 'A'. 156
157 | bar: 2. Enter all task names in column 'A'. 157
158 | bar: 2. Enter all task names in column 'A'. 158
159 | bar: 2. Enter all task names in column 'A'. 159
160 | bar: 2. Enter all task names in column 'A'. 160
161 | bar: 2. Enter all task names in column 'A'. 161
162 | bar: 2. Enter all task names in column 'A'. 162
163 | bar: 2. Enter all task names in column 'A'. 163
164 | bar: 2. Enter all task names in column 'A'. 164
165 | bar: 2. Enter all task names in column 'A'. 165
166 | bar: 2. Enter all task names in column 'A'. 166
167 | bar: 2. Enter all task names in column 'A'. 167
168 | bar: 2. Enter all task names in column 'A'. 168
169 | bar: 2. Enter all task names in column 'A'. 169
170 | bar: 2. Enter all task names in column 'A'. 170
171 | bar: 2. Enter all task names in column 'A'. 171
172 | bar: 2. Enter all task names in column 'A'. 172
173 | bar: 2. Enter all task names in column 'A'. 173
174 | bar: 2. Enter all task names in column 'A'. 174
175 | bar: 2. Enter all task names in column 'A'. 175
176 | bar: 2. Enter all task names in column 'A'. 176
177 | bar: 2. Enter all task names in column 'A'. 177
178 | bar: 2. Enter all task names in column 'A'. 178
179 | bar: 2. Enter all task names in column 'A'. 179
180 | bar: 2. Enter all task names in column 'A'. 180
181 | bar: 2. Enter all task names in column 'A'. 181
182 | bar: 2. Enter all task names in column 'A'. 182
183 | bar: 2. Enter all task names in column 'A'. 183
184 | bar: 2. Enter all task names in column 'A'. 184
185 | bar: 2. Enter all task names in column 'A'. 185
186 | bar: 2. Enter all task names in column 'A'. 186
187 | bar: 2. Enter all task names in column 'A'. 187
188 | bar: 2. Enter all task names in column 'A'. 188
189 | bar: 2. Enter all task names in column 'A'. 189
190 | bar: 2. Enter all task names in column 'A'. 190
191 | bar: 2. Enter all task names in column 'A'. 191
192 | bar: 2. Enter all task names in column 'A'. 192
193 | bar: 2. Enter all task names in column 'A'. 193
194 | bar: 2. Enter all task names in column 'A'. 194
195 | bar: 2. Enter all task names in column 'A'. 195
196 | bar: 2. Enter all task names in column 'A'. 196
197 | bar: 2. Enter all task names in column 'A'. 197
198 | bar: 2. Enter all task names in column 'A'. 198
199 | bar: 2. Enter all task names in column 'A'. 199
200 | bar: 2. Enter all task names in column 'A'. 200
201 | bar: 2. Enter all task names in column 'A'. 201
202 | bar: 2. Enter all task names in column 'A'. 202
203 | bar: 2. Enter all task names in column 'A'. 203
204 | bar: 2. Enter all task names in column 'A'. 204
205 | bar: 2. Enter all task names in column 'A'. 205
206 | bar: 2. Enter all task names in column 'A'. 206
207 | bar: 2. Enter all task names in column 'A'. 207
208 | bar: 2. Enter all task names in column 'A'. 208
209 | bar: 2. Enter all task names in column 'A'. 209
210 | bar: 2. Enter all task names in column 'A'. 210
211 | bar: 2. Enter all task names in column 'A'. 211
212 | bar: 2. Enter all task names in column 'A'. 212
213 | bar: 2. Enter all task names in column 'A'. 213
214 | bar: 2. Enter all task names in column 'A'. 214
215 | bar: 2. Enter all task names in column 'A'. 215
216 | bar: 2. Enter all task names in column 'A'. 216
217 | bar: 2. Enter all task names in column 'A'. 217
218 | bar: 2. Enter all task names in column 'A'. 218
219 | bar: 2. Enter all task names in column 'A'. 219
220 | bar: 2. Enter all task names in column 'A'. 220
221 | bar: 2. Enter all task names in column 'A'. 221
222 | bar: 2. Enter all task names in column 'A'. 222
223 | bar: 2. Enter all task names in column 'A'. 223
224 | bar: 2. Enter all task names in column 'A'. 224
225 | bar: 2. Enter all task names in column 'A'. 225
226 | bar: 2. Enter all task names in column 'A'. 226
227 | bar: 2. Enter all task names in column 'A'. 227
228 | bar: 2. Enter all task names in column 'A'. 228
229 | bar: 2. Enter all task names in column 'A'. 229
230 | bar: 2. Enter all task names in column 'A'. 230
231 | bar: 2. Enter all task names in column 'A'. 231
232 | bar: 2. Enter all task names in column 'A'. 232
233 | bar: 2. Enter all task names in column 'A'. 233
234 | bar: 2. Enter all task names in column 'A'. 234
235 | bar: 2. Enter all task names in column 'A'. 235
236 | bar: 2. Enter all task names in column 'A'. 236
237 | bar: 2. Enter all task names in column 'A'. 237
238 | bar: 2. Enter all task names in column 'A'. 238
239 | bar: 2. Enter all task names in column 'A'. 239
240 | bar: 2. Enter all task names in column 'A'. 240

## Hidden (hidden)
15 | 10 | 2 | 7 | 7
1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 6 | 7
4 | 3 | 4
2 | 9
2 | 4
1 | 5 | 2 | 4 | 1 | 1 | 1
0 | 1 | 0 | 1 | 0 | 0 | 0
0 | 1 | 0 | 2 | 0 | 0 | 0
1 | 3 | 4 | 7 | 10 | 2 | 5 | 13 | 8 | 11 | 12 | 6 | 9 | 14 | 15
1 | 6 | 2 | 3 | 7 | 12 | 4 | 9 | 13 | 5 | 10 | 11 | 8 | 14 | 15
1 | 2 | 2 | 2 | 1 | 1 | 1
1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 6 | 7
1 | 2 | 4 | 6 | 8 | 9 | 10
2 | 6
1 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 6 | 6 | 6 | 7 | 8 | 9 | 10
1 | 2 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15
1 | 1 | 1 | 2 | 3 | 1 | 1
1 | 2 | 3 | 4 | 4 | 5 | 5 | 5 | 6 | 7
1 | 2 | 3 | 4 | 6 | 9 | 10
1 | 4 | 2 | 3 | 7 | 6 | 5 | 8 | 9 | 10
1 | 2
1 | 6 | 7 | 2 | 3 | 4 | 5 | 12 | 9 | 10 | 11 | 8 | 13 | 14 | 15
1 | 3 | 4 | 2 | 7 | 6 | 5 | 8 | 9 | 10
4 | 9
a | Block1: | c | d | g | j | (D) Block1 Duration | b | e | m | Block2: | h | k | l | (D) Block2 Duration | f | i | n | o
1 | 2 | 8 | 9 | 10 | 11 | 16 | 17 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 6 | 0 | 0 | 0 | 0 | 7 | 8 | 9 | 10
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
0 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0
0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0
0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0
0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0
0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0
0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0
0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 1
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 10 | 11 | 17 | 0 | 0 | 0 | 0 | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0
1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 11 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 5 | 6 | 2 | 3 | 4 | 4 | 5 | 5
3
2 | 3
5
4
6 | 7
9
9
8
9
10
4 | 6
9 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
3 | 5 | 9 | 10
6 | 4 | 6 | 7 | 8 | 9 | 10
5 | 6 | 7 | 8 | 9 | 10
2 | 9 | 10
2 | 9 | 10
3 | 8 | 9 | 10
2 | 9 | 10
1 | 10
0

## AEAP
Number of tasks in the DSM : | 15 |  |  | <note> new index used!
Task Name | Level |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
a | 1 | 1 | [15 empty] | 1 | bar: 1
c | 2 | 2 | 1: 2; <note> new index used! 5: 1; <note> new index used! 8: Block1 | 2
d | 2 | 3 | <note> new index used! 2: 2; <note> new index used! 5: 1 | 3
g | 2 | 4 | [15 empty] | 4 | bar: 1 to <note> new index used! 5
j | 2 | 5 | [15 empty] | 5 | bar: <note> new index used! 2 to <note> new index used! 5
b | 2 | 6 | [15 empty] | 6 | bar: 1; <note> new index used! 6
e | 3 | 7 | [15 empty] | 7 | bar: <note> new index used! 6 to <note> new index used! 7
m | 3 | 8 | [15 empty] | 8 | bar: <note> new index used! 4 to <note> new index used! 5; <note> new index used! 8
h | 4 | 9 | <note> new index used! 6: 2; <note> new index used! 7: 1; <note> new index used! 11: 1; <note> new index used! 14: Block2 | 9
k | 4 | 10 | <note> new index used! 9: 2; <note> new index used! 11: 2 | 10
l | 4 | 11 | [15 empty] | 11 | bar: <note> new index used! 9 to <note> new index used! 11
f | 4 | 12 | <note> new index used! 6: 1; <note> new index used! 7: 2 | 12
i | 5 | 13 | <note> new index used! 7: 2; <note> new index used! 12: 1 | 13
n | 6 | 14 | [15 empty] | 14 | bar: <note> new index used! 8; <note> new index used! 11; <note> new index used! 13 to <note> new index used! 14
o | 7 | 15 | [15 empty] | 15 | bar: <note> new index used! 8; <note> new index used! 10; <note> new index used! 14 to <note> new index used! 15
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## ALAP
Number of tasks in the DSM : | 15 |  |  | <note> index based on 'AEAP'
Task Name | Level |  | 1 | 6 | 7 | 2 | 3 | 4 | 5 | 12 | 9 | 10 | 11 | 8 | 13 | 14 | 15
a | 1 | 1 | [15 empty] | 1
b | 2 | 6 | 1 | [14 empty] | 6
e | 3 | 7 |  | 1 | [13 empty] | 7
c | 4 | 2 | 2 | [5 empty] | 1 |  |  | Block1 | [5 empty] | 2
d | 4 | 3 |  |  |  | 2 |  |  | 1 | [8 empty] | 3
g | 4 | 4 | 1 |  |  | 1 | [11 empty] | 4
j | 4 | 5 |  |  |  |  | 1 | 1 | [9 empty] | 5
f | 4 | 12 |  | 1 | 2 | [12 empty] | 12
h | 5 | 9 |  | 2 | 1 | [7 empty] | 1 |  |  | Block2 |  | 9
k | 5 | 10 | [8 empty] | 2 |  | 2 |  |  |  |  | 10
l | 5 | 11 | [9 empty] | 1 | [5 empty] | 11
m | 5 | 8 | [5 empty] | 1 | 1 | [8 empty] | 8
i | 5 | 13 |  |  | 2 |  |  |  |  | 1 | [7 empty] | 13
n | 6 | 14 | [10 empty] | 1 | 1 | 1 |  |  | 14
o | 7 | 15 | [9 empty] | 1 |  | 1 |  | 1 |  | 15
|  |  | 1 | 6 | 7 | 2 | 3 | 4 | 5 | 12 | 9 | 10 | 11 | 8 | 13 | 14 | 15

## AEAP collapsed
Number of elements in the collapsed DSM : | 10 |  |  | <note> new index used!
Task Name | Level |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
a | 1 | 1 | [10 empty] | 1 | bar: 1
Block1: | 2 | 2 | 1: 2 | 2
b | 2 | 3 | [10 empty] | 3 | bar: 1; <note> new index used! 3
e | 3 | 4 | [10 empty] | 4 | bar: <note> new index used! 3 to <note> new index used! 4
m | 3 | 5 | <note> new index used! 2: 2 | 5
Block2: | 4 | 6 | <note> new index used! 3: 2; <note> new index used! 4: 1 | 6
f | 4 | 7 | <note> new index used! 3: 1; <note> new index used! 4: 2 | 7
i | 5 | 8 | <note> new index used! 4: 2; <note> new index used! 7: 1 | 8
n | 6 | 9 | <note> new index used! 5: 1; <note> new index used! 6: 2; <note> new index used! 8: 1 | 9
o | 7 | 10 | <note> new index used! 5: 1; <note> new index used! 6: 2; <note> new index used! 9: 1 | 10
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## ALAP collapsed
Number of elements in the collapsed DSM : | 10 |  |  | <note> Index based on 'AEAP collapsed'
Task Name | Level |  | 1 | 3 | 4 | 2 | 7 | 6 | 5 | 8 | 9 | 10
a | 1 | 1 | [10 empty] | 1
b | 2 | 3 | 1 | [9 empty] | 3
e | 3 | 4 |  | 1 | [8 empty] | 4
Block1: | 4 | 2 | 2 | [9 empty] | 2
f | 4 | 7 |  | 1 | 2 | [7 empty] | 7
Block2: | 5 | 6 |  | 2 | 1 | [7 empty] | 6
m | 5 | 5 |  |  |  | 2 | [6 empty] | 5
i | 5 | 8 |  |  | 2 |  | 1 | [5 empty] | 8
n | 6 | 9 | [5 empty] | 2 | 1 | 1 |  |  | 9
o | 7 | 10 | [5 empty] | 2 | 1 |  | 1 |  | 10
|  |  | 1 | 3 | 4 | 2 | 7 | 6 | 5 | 8 | 9 | 10

## Analysis
Number of elements in the collapsed DSM : | 10 |  |  | <note> index based on AEAP collapsed!
Task Name | Level |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
a | 1 | 1 | [10 empty] | 1 | bar: 1
Block1: | 2 | 2 | 1: 2 | 2
b | 2 | 3 | [10 empty] | 3 | bar: 1; <note> index based on AEAP collapsed! 3
e | 3 | 4 | [10 empty] | 4 | bar: <note> index based on AEAP collapsed! 3 to <note> index based on AEAP collapsed! 4
m | 3 | 5 | <note> index based on AEAP collapsed! 2: 2 | 5
Block2: | 4 | 6 | [10 empty] | 6 | bar: <note> index based on AEAP collapsed! 3 to <note> index based on AEAP collapsed! 4; <note> index based on AEAP collapsed! 6
f | 4 | 7 | <note> index based on AEAP collapsed! 3: 1; <note> index based on AEAP collapsed! 4: 2 | 7
i | 5 | 8 | [10 empty] | 8 | bar: <note> index based on AEAP collapsed! 4; <note> index based on AEAP collapsed! 7 to <note> index based on AEAP collapsed! 8
n | 6 | 9 | <note> index based on AEAP collapsed! 5: 1; <note> index based on AEAP collapsed! 6: 2; <note> index based on AEAP collapsed! 8: 1 | 9
o | 7 | 10 | [10 empty] | 10 | bar: <note> index based on AEAP collapsed! 5 to <note> index based on AEAP collapsed! 6; <note> index based on AEAP collapsed! 9 to <note> index based on AEAP collapsed! 10
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## Resource
Resource Name | Group | % Max Units
A |  | 100%

## Block
Number of Coupled Blocks : | 2
BLOCK1
Duration (with RCs): avg. 29.5 s.d. 10.3
(10%,30%,50%,70%,90%) = (19.1, 22.9, 27.1, 32.7, 43.1) | <Rework Probability>
|  |  | 1st Iteration | [5 empty] | 2nd Iteration | [5 empty] | 3rd Iteration | [5 empty] | 4th Iteration | [5 empty] | 5th Iteration
Task Name | % Decrease | Max.Iteration# |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5
c |  |  | 2 |  |  |  | 0.5 |  | 2 | [5 empty] | 2 | [5 empty] | 2 | [5 empty] | 2
d |  |  | 3 | 0.5 |  |  | 0.5 |  | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3
g |  |  | 4 | 0.5 |  |  |  |  | 4 | [5 empty] | 4 | [5 empty] | 4 | [5 empty] | 4
j |  |  | 5 |  | 0.5 | 0.5 |  |  | 5 | [5 empty] | 5 | [5 empty] | 5 | [5 empty] | 5
<Rework-Adjusted Duration & RPW> | <Learning Curve> |  | <Rework Impact> | [5 empty] | <Overlap Amount> | [5 empty] | <Overlap Impact>
| % Learning | % Max.Learning |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5 |  |  | 2 | 3 | 4 | 5
3.9, 34.1 | 80% | 50% | 2 |  |  |  | 0.6 |  | 2 | [5 empty] | 2
10.8, 26.3 | 80% | 50% | 3 | 0.6 |  |  | 0.6 |  | 3 | [5 empty] | 3
3.9, 19.4 | 80% | 50% | 4 | 0.6 |  |  |  |  | 4 | [5 empty] | 4
15.5, 15.5 | 80% | 50% | 5 |  | 0.6 | 0.6 |  |  | 5 | [5 empty] | 5
BLOCK2
Duration (with RCs): avg. 19.8 s.d. 6.6
(10%,30%,50%,70%,90%) = (13, 15.9, 18.5, 22, 28.5) | <Rework Probability>
Task Name | % Decrease | Max.Iteration# |  | 9 | 10 | 11 |  |  | 9 | 10 | 11 |  |  | 9 | 10 | 11 |  |  | 9 | 10 | 11 |  |  | 9 | 10 | 11
h |  |  | 9 |  |  | 0.5 |  | 9 |  |  |  |  | 9 |  |  |  |  | 9 |  |  |  |  | 9
k |  |  | 10 | 0.5 |  | 0.5 |  | 10 |  |  |  |  | 10 |  |  |  |  | 10 |  |  |  |  | 10
l |  |  | 11 |  | 0.5 |  |  | 11 |  |  |  |  | 11 |  |  |  |  | 11 |  |  |  |  | 11
<Rework-Adjusted Duration & RPW> | <Learning Curve> |  | <Rework Impact> |  |  |  |  | <Overlap Amount> |  |  |  |  | <Overlap Impact>
| % Learning | % Max.Learning |  | 9 | 10 | 11 |  |  | 9 | 10 | 11 |  |  | 9 | 10 | 11
3.9, 19.5 | 80% | 50% | 9 |  |  | 0.6 |  | 9 |  |  |  |  | 9
4.9, 15.6 | 80% | 50% | 10 | 0.6 |  | 0.6 |  | 10 |  |  |  |  | 10
10.7, 10.7 | 80% | 50% | 11 |  | 0.6 |  |  | 11 |  |  |  |  | 11
12.1 | 13.8 | 15.4 | 17.1 | 18.7 | 20.4 | 22 | 23.7 | 25.3 | 27 | 28.6 | 30.3 | 31.9 | 33.6 | 35.2 | 36.9 | 38.5 | 40.2 | 41.8 | 43.5 | 45.1 | 46.8 | 48.4 | 50.1 | 51.7 | 53.4 | 55.1 | 56.7 | 58.4 | 60 | 61.7 | 63.3 | 65 | 66.6 | 68.3 | 69.9 | 71.6 | 73.2 | 74.9 | 76.5 | 78.2 | 79.8 | 81.5 | 83.1 | 84.8 | 86.4 | 88.1 | 89.7 | 91.4 | 93
0 | 0 | 7 | 18 | 55 | 92 | 79 | 94 | 77 | 77 | 63 | 69 | 43 | 53 | 42 | 39 | 21 | 31 | 25 | 19 | 19 | 14 | 9 | 10 | 5 | 5 | 7 | 5 | 4 | 3 | 2 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
0 | 0 | 0.007 | 0.025 | 0.08 | 0.172 | 0.251 | 0.345 | 0.422 | 0.499 | 0.562 | 0.631 | 0.674 | 0.727 | 0.769 | 0.808 | 0.829 | 0.86 | 0.885 | 0.904 | 0.923 | 0.937 | 0.946 | 0.956 | 0.961 | 0.966 | 0.973 | 0.978 | 0.982 | 0.985 | 0.987 | 0.987 | 0.99 | 0.994 | 0.996 | 0.996 | 0.996 | 0.996 | 0.997 | 0.997 | 0.997 | 0.998 | 0.998 | 0.998 | 0.999 | 0.999 | 0.999 | 1 | 1 | 1
5.4 | 6.6 | 7.8 | 9 | 10.2 | 11.4 | 12.6 | 13.8 | 15 | 16.2 | 17.4 | 18.6 | 19.8 | 21 | 22.2 | 23.4 | 24.5 | 25.7 | 26.9 | 28.1 | 29.3 | 30.5 | 31.7 | 32.9 | 34.1 | 35.3 | 36.5 | 37.7 | 38.9 | 40.1 | 41.3 | 42.5 | 43.7 | 44.8 | 46 | 47.2 | 48.4 | 49.6 | 50.8 | 52 | 53.2 | 54.4 | 55.6 | 56.8 | 58 | 59.2 | 60.4 | 61.6 | 62.8 | 64
0 | 0 | 0 | 2 | 13 | 27 | 44 | 77 | 73 | 86 | 103 | 84 | 74 | 63 | 70 | 56 | 41 | 33 | 33 | 15 | 17 | 13 | 19 | 12 | 7 | 9 | 5 | 4 | 6 | 3 | 3 | 2 | 3 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
0 | 0 | 0 | 0.002 | 0.015 | 0.042 | 0.086 | 0.163 | 0.236 | 0.322 | 0.425 | 0.509 | 0.583 | 0.646 | 0.716 | 0.772 | 0.813 | 0.846 | 0.879 | 0.894 | 0.911 | 0.924 | 0.943 | 0.955 | 0.962 | 0.971 | 0.976 | 0.98 | 0.986 | 0.989 | 0.992 | 0.994 | 0.997 | 0.997 | 0.998 | 0.998 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 0.999 | 1 | 1 | 1 | 1

## GanttChart(B1)
<NOTE> 1. The number inside a bar indicates the overlap amount of a task executed in prior state(s). 2. 'Task ID' is based on the ID in 'Project' spreadsheet.
|  | <Scenario 1 of Block 1> | [7 empty] | <Scenario 2 of Block 1> | [6 empty] | <Scenario 3 of Block 1>
Task ID | Task Name | Sampled Duration | Simulated Duration | [6 empty] | Sampled Duration | Simulated Duration | [5 empty] | Sampled Duration | Simulated Duration
3 | c | 2.8 | 4.1 | [6 empty] | 4.8 | 4.8 | [5 empty] | 4.3 | 4.3
4 | d | 12.5 | 18.5 | [6 empty] | 14.8 | 21.9 | [5 empty] | 9.1 | 13.5
5 | g | 4.3 | 4.3 | [6 empty] | 5.2 | 5.2 | [5 empty] | 6.4 | 6.4
6 | j | 5 | 5 | [6 empty] | 9 | 9 | [5 empty] | 3.9 | 5.8
|  |  | State | 1 | 2 | 3 | 4 | 5 | 6 |  | State | 1 | 2 | 3 | 4 | 5 |  | State | 1 | 2 | 3 | 4 | 5 | 6
|  |  | State Duration | 2.8 | 4.3 | 8.2 | 5 | 1.3 | 6 |  | State Duration | 4.8 | 5.2 | 9.6 | 9 | 7.1 |  | State Duration | 4.3 | 6.4 | 2.7 | 3.9 | 4.4 | 1.9
|  |  | Lead Time | 27.6 | [6 empty] | Lead Time | 35.7 | [5 empty] | Lead Time | 23.6

## GanttChart(B2)
<NOTE> 1. The number inside a bar indicates the overlap amount of a task executed in prior state(s). 2. 'Task ID' is based on the ID in 'Project' spreadsheet.
|  | <Scenario 1 of Block 2> | [6 empty] | <Scenario 2 of Block 2> |  |  |  |  | <Scenario 3 of Block 2>
Task ID | Task Name | Sampled Duration | Simulated Duration | [5 empty] | Sampled Duration | Simulated Duration |  |  |  | Sampled Duration | Simulated Duration
12 | h | 2.2 | 3.3 | [5 empty] | 4 | 4 |  |  |  | 0.4 | 0.6
13 | k | 4.2 | 7.56 | [5 empty] | 6.2 | 6.2 |  |  |  | 4.5 | 8.1
14 | l | 6.2 | 6.2 | [5 empty] | 5.2 | 5.2 |  |  |  | 4.4 | 4.4
|  |  | State | 1 | 2 | 3 | 4 | 5 |  | State | 1 | 2 | 3 |  | State | 1 | 2 | 3 | 4 | 5
|  |  | State Duration | 2.2 | 4.2 | 6.2 | 1.1 | 3.4 |  | State Duration | 4 | 6.2 | 5.2 |  | State Duration | 0.4 | 4.5 | 4.4 | 0.2 | 3.6
|  |  | Lead Time | 17.1 | [5 empty] | Lead Time | 15.4 |  |  |  | Lead Time | 13.1

## MS Project
Task ID | Task Name | Opt Duration | Likely Duration | Pess Duration | % Complete | Act Duration | Predecessors | Resource Names | Priority | Slack(avg,sd) | %Criticality | RC_Slack(avg,sd) | %RC_Criticality | CUMRED | RED | Slack/Suc
1 | a | 4 | 5 | 6 | [5 empty] | 0, 0 | 100 | 0, 0 | 100 | 29.7 | 0 | 0
2 | Block1: | [5 empty] | 1 |  |  | 4.4, 6.4 | 45 | 8.4, 7.8 | 19 | 7 | 0 | 0
3 | c | 3 | 4 | 5
4 | d | 9 | 10 | 13 |  |  | 3FS
5 | g | 2 | 4 | 6 |  |  | 3
6 | j | 3 | 5 | 9 |  |  | 4, 5
7 | (D) Block1 Duration | 19.1 | 27.1 | 43.1
8 | b | 5 | 6 | 8 |  |  | 1 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 81 | 22.7 | 0 | 0.2
9 | e | 8 | 9 | 11 |  |  | 8 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 81 | 22.7 | 0 | 0.3
10 | m | 4[20%] | 7 | 10 |  |  | 2 | A |  | 4.4, 6.4 | 45 | 0, 0 | 100 | 7 | 7 | 0
11 | Block2: | [5 empty] | 9 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 82 | 19.7 | 19.7 | 0.8
12 | h | 2 | 4 | 6
13 | k | 4 | 5 | 6 |  |  | 12FS
14 | l | 3 | 5 | 9 |  |  | 13
15 | (D) Block2 Duration | 13 | 18.5 | 28.5 |  |  |  | A
16 | f | 4 | 5 | 6 |  |  | 9 |  |  | 15.9, 9.4 | 0 | 21.2, 8.2 | 0 | 3 | 0 | 4.5
17 | i | 2 | 3 | 5 |  |  | 16 | A |  | 15.9, 9.4 | 0 | 1.6, 5.2 | 82 | 3 | 3 | 6.7
18 | n | 5 | 8 | 12 |  |  | 10, 11, 17 |  |  | 0, 0 | 100 | 0, 0 | 100 | 0 | 0 | 0
19 | o | 3 | 5 | 8 |  |  | 18 |  |  | 0, 0 | 100 | 0, 0 | 100 | 0 | 0 | 0

## Project
Task ID | Task Name | Opt Duration | Likely Duration | Pess Duration | % Complete | Act Duration | Predecessors | Resource Names | Priority | Slack(avg,sd) | %Criticality | RC_Slack(avg,sd) | %RC_Criticality | CUMRED | RED | Slack/Suc | Lead Time (without Resource Constraints) | 38.3 | 39.9 | 41.6 | 43.2 | 44.9 | 46.5 | 48.2 | 49.8 | 51.4 | 53.1 | 54.7 | 56.4 | 58 | 59.7 | 61.3 | 63 | 64.6 | 66.2 | 67.9 | 69.5 | 71.2 | 72.8 | 74.5 | 76.1 | 77.8 | 79.4 | 81 | 82.7 | 84.3 | 86 | 87.6 | 89.3 | 90.9 | 92.5 | 94.2 | 95.8 | 97.5 | 99.1 | 100.8 | 102.4 | 104.1 | 105.7 | 107.3 | 109 | 110.6 | 112.3 | 113.9 | 115.6 | 117.2 | 118.9
1 | a | 4 | 5 | 6 | [5 empty] | 0, 0 | 100 | 0, 0 | 100 | 29.7 | 0 | 0 | Avg 59.4, Std 10.2 | 0 | 0 | 2 | 3 | 20 | 29 | 41 | 51 | 49 | 86 | 75 | 79 | 77 | 69 | 57 | 55 | 58 | 40 | 37 | 33 | 30 | 18 | 13 | 14 | 17 | 6 | 7 | 8 | 7 | 5 | 2 | 2 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0
2 | Block1: | [5 empty] | 1 |  |  | 4.4, 6.4 | 45 | 8.4, 7.8 | 19 | 7 | 0 | 0 | (10%,30%,50%,70%,90%) = (48.5, 53.6, 57.8, 63.2, 72.1) | 0 | 0 | 0.002 | 0.005 | 0.025 | 0.054 | 0.095 | 0.146 | 0.195 | 0.281 | 0.356 | 0.435 | 0.512 | 0.581 | 0.638 | 0.693 | 0.751 | 0.791 | 0.828 | 0.861 | 0.891 | 0.909 | 0.922 | 0.936 | 0.953 | 0.959 | 0.966 | 0.974 | 0.981 | 0.986 | 0.988 | 0.99 | 0.993 | 0.995 | 0.996 | 0.996 | 0.996 | 0.996 | 0.996 | 0.996 | 0.996 | 0.997 | 0.997 | 0.997 | 0.997 | 0.998 | 0.998 | 1 | 1 | 1
3 | c | 3 | 4 | 5 | [12 empty] | Major Critical Paths (without Resource Constraints) | 43.6 | 45.1 | 46.6 | 48.1 | 49.6 | 51.1 | 52.6 | 54.1 | 55.6 | 57.1 | 58.6 | 60.1 | 61.6 | 63.1 | 64.6 | 66.1 | 67.5 | 69 | 70.5 | 72 | 73.5 | 75 | 76.5 | 78 | 79.5 | 81 | 82.5 | 84 | 85.5 | 87 | 88.5 | 90 | 91.5 | 92.9 | 94.4 | 95.9 | 97.4 | 98.9 | 100.4 | 101.9 | 103.4 | 104.9 | 106.4 | 107.9 | 109.4 | 110.9 | 112.4 | 113.9 | 115.4 | 116.9
4 | d | 9 | 10 | 13 |  |  | 3FS | [9 empty] | 1-8-9-11-18-19 [54%] | 0 | 2 | 0 | 2 | 7 | 7 | 15 | 20 | 38 | 50 | 48 | 64 | 70 | 87 | 67 | 63 | 56 | 61 | 71 | 45 | 43 | 38 | 22 | 25 | 16 | 14 | 19 | 12 | 5 | 7 | 8 | 4 | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0
5 | g | 2 | 4 | 6 |  |  | 3 | [9 empty] | 1-2-10-18-19 [44%] | 0 | 0.002 | 0.002 | 0.004 | 0.011 | 0.018 | 0.033 | 0.053 | 0.091 | 0.141 | 0.189 | 0.253 | 0.323 | 0.41 | 0.477 | 0.54 | 0.596 | 0.657 | 0.728 | 0.773 | 0.816 | 0.854 | 0.876 | 0.901 | 0.917 | 0.931 | 0.95 | 0.962 | 0.967 | 0.974 | 0.982 | 0.986 | 0.992 | 0.993 | 0.994 | 0.994 | 0.995 | 0.995 | 0.995 | 0.995 | 0.995 | 0.996 | 0.997 | 0.997 | 0.997 | 0.998 | 0.998 | 0.998 | 1 | 1
6 | j | 3 | 5 | 9 |  |  | 4, 5
7 | (D) Block1 Duration | 19.1 | 27.1 | 43.1
8 | b | 5 | 6 | 8 |  |  | 1 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 81 | 22.7 | 0 | 0.2 | Lead Time (with Leveled Resources)
9 | e | 8 | 9 | 11 |  |  | 8 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 81 | 22.7 | 0 | 0.3 | Avg 66.3, Std 9.3
10 | m | 4[20%] | 7 | 10 |  |  | 2 | A |  | 4.4, 6.4 | 45 | 0, 0 | 100 | 7 | 7 | 0 | (10%,30%,50%,70%,90%) = (56.1, 61.2, 65.2, 70.1, 77.9)
11 | Block2: | [5 empty] | 9 |  |  | 4.6, 8.2 | 55 | 1.6, 5.2 | 82 | 19.7 | 19.7 | 0.8 | Major Critical Sequences (with Leveled Resources)
12 | h | 2 | 4 | 6 | [12 empty] | 1-8-9-11-10-17-18-19 [74%]
13 | k | 4 | 5 | 6 |  |  | 12FS | [9 empty] | 1-2-10-18-19 [17%]
14 | l | 3 | 5 | 9 |  |  | 13 | [9 empty] | 1-8-9-11-17-10-18-19 [5%]
15 | (D) Block2 Duration | 13 | 18.5 | 28.5 |  |  |  | A
16 | f | 4 | 5 | 6 |  |  | 9 |  |  | 15.9, 9.4 | 0 | 21.2, 8.2 | 0 | 3 | 0 | 4.5
17 | i | 2 | 3 | 5 |  |  | 16 | A |  | 15.9, 9.4 | 0 | 1.6, 5.2 | 82 | 3 | 3 | 6.7
18 | n | 5 | 8 | 12 |  |  | 10, 11, 17 |  |  | 0, 0 | 100 | 0, 0 | 100 | 0 | 0 | 0
19 | o | 3 | 5 | 8 |  |  | 18 |  |  | 0, 0 | 100 | 0, 0 | 100 | 0 | 0 | 0

## GanttChart(P1)
<NOTE> 1. The number inside a bar indicates the overlap amount of a task executed in prior state(s). 2. 'Task ID' is the ID used in 'Project' spreadsheet for MS Project.
|  | <Scenario 1 of entire project without resource constraints> | [10 empty] | <Scenario 2> | [10 empty] | <Scenario 3>
Task ID | Task Name | Simulated Duration | [10 empty] | Simulated Duration | [10 empty] | Simulated Duration
1 | a | 5.5 | [10 empty] | 4.9 | [10 empty] | 4
2 | Block1: | 27.6 | [10 empty] | 35.7 | [10 empty] | 23.6
8 | b | 5 | [10 empty] | 6.2 | [10 empty] | 8.5
9 | e | 9.6 | [10 empty] | 9.3 | [10 empty] | 11
10 | m | 8.2 | [10 empty] | 7 | [10 empty] | 2.1
11 | Block2: | 17.1 | [10 empty] | 15.4 | [10 empty] | 13.1
16 | f | 3.9 | [10 empty] | 4 | [10 empty] | 5.3
17 | i | 2 | [10 empty] | 3.6 | [10 empty] | 4.3
18 | n | 7.9 | [10 empty] | 8.9 | [10 empty] | 8.4
19 | o | 5 | [10 empty] | 5.6 | [10 empty] | 8.8
|  | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | State Duration | 5.5 | 5 | 9.6 | 3.9 | 2 | 7.1 | 4.1 | 4.1 | 7.9 | 5 | State Duration | 4.9 | 6.2 | 9.3 | 4 | 3.6 | 7.8 | 4.8 | 7 | 8.9 | 5.6 | State Duration | 4 | 8.5 | 11 | 4.1 | 1.2 | 0.9 | 3.4 | 3.5 | 8.4 | 8.8
|  | Lead Time | 54.2 | [9 empty] | Lead Time | 62.1 | [9 empty] | Lead Time | 53.8

## GanttChart(P2)
<NOTE> 1. The number inside a bar indicates the overlap amount of a task executed in prior state(s). 2. 'Task ID' is the ID used in 'Project' spreadsheet for MS Project.
|  | <Scenario 1 of entire project with leveled resources> | [10 empty] | <Scenario 2> | [10 empty] | <Scenario 3>
Task ID | Task Name | Simulated Duration | [10 empty] | Simulated Duration | [10 empty] | Simulated Duration
1 | a | 5.5 | [10 empty] | 4.9 | [10 empty] | 4
2 | Block1: | 27.6 | [10 empty] | 35.7 | [10 empty] | 23.6
8 | b | 5 | [10 empty] | 6.2 | [10 empty] | 8.5
9 | e | 9.6 | [10 empty] | 9.3 | [10 empty] | 11
10 | m | 8.2 | [10 empty] | 7 | [10 empty] | 2.1
11 | Block2: | 17.1 | [10 empty] | 15.4 | [10 empty] | 13.1
16 | f | 3.9 | [10 empty] | 4 | [10 empty] | 5.3
17 | i | 2 | [10 empty] | 3.6 | [10 empty] | 4.3
18 | n | 7.9 | [10 empty] | 8.9 | [10 empty] | 8.4
19 | o | 5 | [10 empty] | 5.6 | [10 empty] | 8.8
|  | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | State | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  | State Duration | 5.5 | 5 | 9.6 | 3.9 | 9.1 | 4.1 | 8.2 | 2 | 7.9 | 5 | State Duration | 4.9 | 6.2 | 9.3 | 4 | 11.4 | 3.6 | 1.2 | 7 | 8.9 | 5.6 | State Duration | 4 | 8.5 | 11 | 4.1 | 1.2 | 7.8 | 2.1 | 4.3 | 8.4 | 8.8
|  | Lead Time | 60.3 | [9 empty] | Lead Time | 62.1 | [9 empty] | Lead Time | 60.2