## Definitions
Source Atom | Atom Kind | Property Duration
Define Competitive Requirements | Req | 1
Define New Market Requirements | Req | 2
Define Upgrade Requirements | Req | 2
Determine Compatibility | Analysis | 2
Determine Training | Analysis | 2
Determine Load | Analysis | 4
Determine Strength Needed | Analysis | 4
Determine Power Need | Analysis | 3
Determine Cost | Analysis | 6
Determine Manufacturability | Analysis | 2
Design Frame Structure | Design | 8
Design Hydraulic System | Design | 8

## Dependencies
Source Atom | Target Atom | Dependency Strength | Dependency Kind | Dependency Property Risk
Determine Compatibility | Define Upgrade Requirements | 1 | default | high
Determine Training | Define New Market Requirements | 1 | default | low
Determine Training | Define Upgrade Requirements | 1 | default | low
Determine Load | Define New Market Requirements | 1 | default | med
Determine Load | Define Upgrade Requirements | 1 | default | high
Determine Load | Determine Cost | 1 | default | high
Determine Strength Needed | Determine Load | 1 | default | med
Determine Power Need | Define New Market Requirements | 1 | default | med
Determine Power Need | Define Upgrade Requirements | 1 | default | med
Determine Power Need | Determine Compatibility | 1 | default | med
Determine Power Need | Determine Load | 1 | default | high
Determine Cost | Define Competitive Requirements | 1 | default | high
Determine Cost | Define New Market Requirements | 1 | default | med
Determine Cost | Define Upgrade Requirements | 1 | default | low
Determine Cost | Determine Compatibility | 1 | default | low
Determine Cost | Determine Load | 1 | default | low
Determine Cost | Determine Strength Needed | 1 | default | low
Determine Cost | Determine Power Need | 1 | default | med
Determine Manufacturability | Determine Load | 1 | default | med
Determine Manufacturability | Determine Cost | 1 | default | low
Design Frame Structure | Determine Compatibility | 1 | default | high
Design Frame Structure | Determine Load | 1 | default | high
Design Frame Structure | Determine Cost | 1 | default | low
Design Frame Structure | Determine Manufacturability | 1 | default | med
Design Hydraulic System | Determine Cost | 1 | default | med
Design Hydraulic System | Design Frame Structure | 1 | default | med